## Test Cases
Test Case ID | Requirement ID | Scenario | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID | Tester | Test Date | Comments
TC-001 | TL-FR-001, TL-FR-002 | Create a controlled mortgage-forbearance case with all mandatory information | Authorised mortgage case operator is logged in and has access to create a case | 1. Select Create Case. 2. Enter all mandatory customer, account and case information. 3. Save the case. | A new case is created successfully, a unique case identifier is generated, the case is saved in Draft status, and the operator and creation timestamp are recorded. |  | Not Run
TC-002 | TL-FR-003, TL-RULE-001 | Attempt to progress a case with missing mandatory information | Authorised mortgage case operator is logged in and a Draft case exists | 1. Open the Draft case. 2. Leave one mandatory field blank. 3. Attempt to progress the case to assessment. | The system identifies the missing mandatory information, clearly informs the operator what is missing, and prevents the case from progressing to assessment unless an authorised exception is recorded. |  | Not Run
TC-003 | TL-FR-007, TL-FR-008, TL-RULE-005 | Attempt to approve a case by the same user who created it | A mortgage-forbearance case has been created and submitted for approval by the case originator | 1. Sign in as the same user who created the case. 2. Open the submitted case. 3. Attempt to approve the case. | The system prevents the case originator from approving their own case where separation of duties applies, and the blocked approval attempt is recorded. |  | Not Run
TC-004 | TL-FR-011, TL-RULE-006 | Attempt to execute a decision version that does not match the approved version | Decision version 3 has been approved and is ready for execution | 1. Submit an execution request for decision version 4. 2. Allow TraceLogic to validate the requested version against the approved version. | Execution is blocked because the requested decision version does not match the approved decision version, and the mismatch is recorded in the audit history. |  | Not Run
TC-005 | TL-FR-011, TL-FR-012, TL-RULE-006 | Execute the exact approved decision version successfully | Decision version 3 has been approved and remains valid | 1. Submit an execution request for decision version 3. 2. Allow TraceLogic to validate the requested version. 3. Execute the approved arrangement. | The version check succeeds, execution is permitted, the approved arrangement is implemented, and the execution result and reference are recorded. |  | Not Run
TC-006 | TL-RULE-007, TL-EX-004 | Change material case information after approval | A mortgage-forbearance decision has already been approved | 1. Open the approved case. 2. Change a field classified as material. 3. Save the updated case. 4. Attempt to execute the previously approved decision. | The previous approval is invalidated, execution is blocked, and the case requires reassessment and new approval. |  | Not Run
TC-007 | TL-EX-002, TL-RULE-004 | Submit a policy exception without required approval | A case has failed a policy rule and an exception has been recorded | 1. Record the exception reason. 2. Attempt to progress the case without an authorised exception approval. | The system prevents normal progression until the exception is reviewed and approved by a user with the required authority. |  | Not Run
TC-008 | TL-EX-006 | Attempt to reuse an execution authorisation that has already been used | A valid execution authorisation has already been used successfully once | 1. Resubmit the same execution authorisation. 2. Attempt to execute the decision again. | The second execution attempt is blocked because the authorisation has already been used, and the attempt is recorded. |  | Not Run
TC-009 | TL-EX-005, TL-FR-012 | Execution fails in the mortgage servicing system | A valid approved decision has passed the exact-version check | 1. Submit the valid approved decision for execution. 2. Simulate a servicing-system execution failure. 3. Return the failure result to TraceLogic. | The execution is recorded as failed, the case is not treated as successfully completed, and the failure is available for investigation. |  | Not Run
TC-010 | TL-FR-013, TL-FR-014, TL-NFR-005, TL-NFR-006 | Reconstruct the complete decision history for a completed case | A mortgage-forbearance case has been created, assessed, approved and executed | 1. Sign in as an authorised audit or compliance reviewer. 2. Open the completed case. 3. Review the decision history. | The reviewer can see the material actions, timestamps, users or systems involved, policy version, rule results, rationale, approval details, approved version and execution result in chronological order. |  | Not Run
TC-011 | TL-FR-006, TL-RULE-003 | Attempt to submit a proposed outcome without a recorded rationale | A mortgage-forbearance case has been assessed and a proposed outcome has been selected | 1. Leave the decision rationale blank. 2. Attempt to submit the case for approval. | Submission is blocked because the proposed decision does not contain a recorded rationale, and the user is prompted to provide one. |  | Not Run
TC-012 | TL-FR-009 | Review a submitted case and use each supported approval outcome | A complete case has been submitted to an authorised approver | 1. Open the submitted case. 2. Confirm the Approve option is available. 3. Confirm the Reject option is available. 4. Confirm the Return for further information option is available. 5. Verify that rejecting or returning requires a reason or comment. | The authorised approver can approve, reject or return the case. Rejection and return actions require the relevant reason or comment to be recorded. |  | Not Run
TC-013 | TL-RULE-008, TL-FR-010 | Change an approved decision and create a new controlled decision version | A mortgage-forbearance decision has already been approved and has a recorded decision version | 1. Open the approved case. 2. Change a material element of the approved decision. 3. Save the change. 4. Review the decision history and version information. | The approved decision is not overwritten. A new controlled decision version is created, the previous version remains in the history, and the new version requires appropriate reassessment and approval before execution. |  | Not Run

## Traceability Matrix
Requirement ID | Requirement Description | Jira Story | Acceptance Criteria | Test Case ID | Coverage Status | Comments | Column1
TL-BR-001 | Apply a consistent and controlled mortgage-forbearance assessment process. | SCRUM-1, SCRUM-2, SCRUM-3 |  |  | Story Mapped | Mapped in TL-E03; test coverage is through linked functional requirements/rules.
TL-BR-002 | Demonstrate which customer information, policy criteria and approvals supported each decision. | SCRUM-3, SCRUM-8 |  |  | Story Mapped | Mapped in TL-E03; test coverage is through linked functional/NFR items.
TL-BR-003 | Ensure only appropriately authorised users approve controlled decisions. | SCRUM-4, SCRUM-5 |  |  | Story Mapped | Mapped in TL-E03; test coverage is through approval controls.
TL-BR-004 | Preserve a traceable record of the decision from intake through implementation. | SCRUM-1, SCRUM-6, SCRUM-8 |  |  | Story Mapped | Mapped in TL-E03; test coverage is through execution/audit requirements.
TL-BR-005 | Reduce avoidable rework caused by missing information, incomplete checks or absent approval evidence. | SCRUM-2, SCRUM-7 |  |  | Story Mapped | Mapped in TL-E03; direct business-outcome measurement is not part of current test design.
TL-BR-006 | Provide reliable management information on case volumes, outcomes, exceptions and delays. | SCRUM-7 |  |  | Story Mapped | Mapped in TL-E03; direct reporting test not yet defined.
TL-FR-001 | Allow an authorised operator to create a mortgage-forbearance case. | SCRUM-1 – Capture a controlled mortgage-forbearance case | Authorised operator can create a case; unique ID and Draft status recorded. | TC-001 | Mapped | Positive-path test designed.
TL-FR-002 | Capture mandatory customer, account and assessment information. | SCRUM-1 – Capture a controlled mortgage-forbearance case | Mandatory customer, account and assessment information can be recorded. | TC-001 | Mapped | Positive-path test designed.
TL-FR-003 | Identify missing mandatory information before assessment proceeds. | SCRUM-2 – Validate mandatory case information | Missing mandatory information is identified and blocks progression. | TC-002 | Mapped | Negative-path test designed.
TL-FR-004 | Evaluate the case against the applicable policy criteria. | SCRUM-3 – Evaluate the case against policy criteria | Applicable policy criteria are evaluated. | TC-007 | Partial | Current test covers the exception path, not a direct positive policy-evaluation scenario.
TL-FR-005 | Record the policy version and rule results used during assessment. | SCRUM-3 – Evaluate the case against policy criteria | Policy version and rule results are recorded with the decision. | TC-010 | Partial | Audit scenario checks visibility; direct recording test not yet defined.
TL-FR-006 | Record the proposed outcome and supporting rationale. | SCRUM-3 – Evaluate the case against policy criteria | A proposed outcome contains a recorded rationale before submission. | TC-011 | Mapped | Direct negative rationale test added.
TL-FR-007 | Route cases requiring approval to an authorised approver. | SCRUM-4 – Submit the proposed outcome for independent approval | Cases meeting approval criteria are routed to an authorised approver. | TC-003, TC-007 | Partial | Control tests exist; direct routing test not yet defined.
TL-FR-008 | Prevent the case originator from approving their own case where separation of duties applies. | SCRUM-4 – Submit the proposed outcome for independent approval | Self-approval is blocked where separation of duties applies. | TC-003 | Mapped | Direct negative-control test.
TL-FR-009 | Allow an approver to approve, reject or return a case for further information. | SCRUM-5 – Review and decide a submitted case | Approver can approve, reject or return a case, with relevant reason/comment where required. | TC-012 | Mapped | Direct approval-outcome test added.
TL-FR-010 | Record the final approved decision and its exact version. | SCRUM-5 / SCRUM-6 | Approval records the final decision and exact approved version. | TC-004, TC-005, TC-006, TC-013 | Mapped | Version-dependent scenarios designed.
TL-FR-011 | Prevent execution of a decision that does not match the approved version. | SCRUM-6 – Execute only the approved decision version | Execution is allowed only when the requested version matches the approved version. | TC-004, TC-005, TC-006 | Mapped | Core exact-version control covered.
TL-FR-012 | Record the implementation or execution outcome. | SCRUM-6 – Execute only the approved decision version | Successful or failed execution outcome is recorded. | TC-005, TC-009 | Mapped | Success and failure paths covered.
TL-FR-013 | Retain an audit trail of material actions and status changes. | SCRUM-1 / SCRUM-8 | Material actions include actor/system, timestamp and action. | TC-010 | Mapped | Audit-history scenario designed.
TL-FR-014 | Allow authorised users to review the full decision history. | SCRUM-8 – Reconstruct the complete decision history | Authorised reviewer can reconstruct the decision history. | TC-010 | Mapped | Direct reconstruction scenario.
TL-FR-015 | Provide management reporting on case status, outcomes, exceptions and processing time. | SCRUM-7 – Monitor case progress and control exceptions |  |  | Gap | Mapped to Jira in TL-E03; no direct reporting test scenario currently defined.
TL-RULE-001 | Case must not proceed to assessment until mandatory information is present or an authorised exception is recorded. | SCRUM-2 | Incomplete mandatory information blocks progression. | TC-002 | Mapped | Direct negative-path test.
TL-RULE-002 | Policy version used for assessment must be recorded with the decision. | SCRUM-3 | Policy version is recorded with the decision. | TC-010 | Partial | Visible in audit reconstruction; direct recording test not yet defined.
TL-RULE-003 | Each decision must include a recorded rationale. | SCRUM-3 | Submission is blocked if rationale is absent. | TC-011 | Mapped | Direct negative rationale test.
TL-RULE-004 | Cases meeting defined escalation criteria must be referred to an authorised approver. | SCRUM-4 | Case requiring approval is referred to an authorised approver. | TC-003, TC-007 | Partial | Authority/control tests exist; direct routing scenario not yet defined.
TL-RULE-005 | User must not approve a case they originated where separation of duties is required. | SCRUM-4 | Self-approval is blocked. | TC-003 | Mapped | Direct control test.
TL-RULE-006 | Approved decision must be the same version presented for execution. | SCRUM-6 | Exact match permits execution; mismatch blocks execution. | TC-004, TC-005 | Mapped | Central project control.
TL-RULE-007 | Approval must not remain valid after a material case change. | SCRUM-5 | Material change requires reassessment and new approval. | TC-006 | Mapped | Direct stale-approval scenario.
TL-RULE-008 | Final decision must not be altered without creating a new controlled version. | SCRUM-6 | Changed final decision creates a new controlled version. | TC-013 | Mapped | Direct controlled-version scenario added.
TL-RULE-009 | Implementation result must be linked to the approved decision record. | SCRUM-6 / SCRUM-8 | Execution outcome remains associated with the approved decision. | TC-005, TC-009 | Mapped | Success and failure paths designed.
TL-RULE-010 | All material case actions must record user, timestamp and action performed. | SCRUM-8 | Audit history records actor/system, action and timestamp. | TC-010 | Mapped | Audit scenario designed.
TL-EX-001 | Missing mandatory information may proceed only where policy permits it and an authorised user records the reason. | SCRUM-2 | Authorised exception is required before incomplete case progression. | TC-002 | Partial | TC-002 tests blocking but does not exercise the authorised-exception route.
TL-EX-002 | Policy exception requires reason, evidence and approval by a user with the required authority. |  | Policy exception cannot progress without authorised review and approval. | TC-007 | Mapped | Direct exception-control scenario.
TL-EX-003 | Returned case must re-enter the controlled process at the appropriate earlier stage. |  |  |  | Gap | Defined in TL-E02; no direct Jira mapping or test scenario documented in TL-E03/current test pack.
TL-EX-004 | Material change after approval invalidates earlier approval and requires reassessment. |  | Material change requires reassessment and new approval before execution. | TC-006 | Mapped | Direct stale-approval scenario.
TL-EX-005 | Failed execution must be recorded and not treated as a completed customer outcome. | SCRUM-6 | Failed execution is recorded and case is not treated as successfully completed. | TC-009 | Mapped | Direct execution-failure scenario.
TL-EX-006 | Expired or previously used execution authorisation must not permit execution. | SCRUM-6 | Invalid or reused authorisation is blocked. | TC-008 | Mapped | Direct duplicate-authorisation scenario.
TL-NFR-001 | Access restricted according to defined user roles and permissions. |  |  |  | Gap | Defined in TL-E02; no direct TL-E03/test mapping documented.
TL-NFR-002 | Customer information protected in transit and at rest. |  |  |  | Gap | Defined in TL-E02; no direct TL-E03/test mapping documented.
TL-NFR-003 | Tenant or business-unit data isolated from unauthorised users. |  |  |  | Gap | Defined in TL-E02; no direct TL-E03/test mapping documented.
TL-NFR-004 | Decision evidence and audit records protected against unauthorised alteration. |  |  |  | Gap | Defined in TL-E02; no direct TL-E03/test mapping documented.
TL-NFR-005 | Material actions timestamped and attributable to a specific user or system. | SCRUM-8 | Audit history identifies actor/system, action and timestamp. | TC-010 | Mapped | Auditability coverage.
TL-NFR-006 | Preserve sufficient evidence to reconstruct the decision path. | SCRUM-8 | Reviewer can reconstruct evidence, rules, rationale, approval and execution history. | TC-010 | Mapped | Decision-reconstruction coverage.
TL-NFR-007 | Display clear validation and error messages. |  |  |  | Gap | Defined in TL-E02; direct usability test not yet defined.
TL-NFR-008 | Core case pages usable on standard desktop screen sizes. |  |  |  | Gap | Defined in TL-E02; direct usability test not yet defined.
TL-NFR-009 | Authorised case information loads within an agreed operational response time under normal conditions. |  |  |  | Gap | Performance target remains an open issue in TL-E02.
TL-NFR-010 | Retain records according to the approved retention schedule. |  |  |  | Gap | Retention period remains an open issue in TL-E02.
TL-NFR-011 | Provide appropriate logging and monitoring for operational support. |  |  |  | Gap | Defined in TL-E02; direct supportability test not yet defined.
TL-NFR-012 | Policy and rule changes are version controlled. |  |  |  | Gap | Defined in TL-E02; direct maintainability test not yet defined.

## Requirements Register
Requirement ID | Requirement Type | Requirement Description | Source / Rationale | Priority | Status | Related Process Step | Related Rule ID | Comments
TL-FR-001 | Functional | The solution shall allow an authorised operator to create a mortgage-forbearance case. | Supports controlled case intake. | Must | Draft | Case creation |  | TL-E02
TL-FR-002 | Functional | The solution shall capture mandatory customer, account and assessment information. | Supports complete case assessment. | Must | Draft | Case creation | TL-RULE-001 | TL-E02
TL-FR-003 | Functional | The solution shall identify missing mandatory information before assessment proceeds. | Supports evidence-validation control. | Must | Draft | Evidence validation | TL-RULE-001 | TL-E02
TL-FR-004 | Functional | The solution shall evaluate the case against the applicable policy criteria. | Supports policy evaluation. | Must | Draft | Policy evaluation | TL-RULE-002 | TL-E02
TL-FR-005 | Functional | The solution shall record the policy version and rule results used during assessment. | Supports later reconstruction of the decision. | Must | Draft | Policy evaluation | TL-RULE-002 | TL-E02
TL-FR-006 | Functional | The solution shall record the proposed outcome and supporting rationale. | Links assessment to the proposed decision. | Must | Draft | Assessment outcome | TL-RULE-003 | TL-E02
TL-FR-007 | Functional | The solution shall route cases requiring approval to an authorised approver. | Supports independent approval. | Must | Draft | Approval | TL-RULE-004 | TL-E02
TL-FR-008 | Functional | The solution shall prevent the case originator from approving their own case where separation of duties applies. | Supports segregation of duties. | Must | Draft | Approval | TL-RULE-005 | TL-E02
TL-FR-009 | Functional | The solution shall allow an approver to approve, reject or return a case for further information. | Supports controlled approval outcomes. | Must | Draft | Approval | TL-RULE-004 | TL-E02
TL-FR-010 | Functional | The solution shall record the final approved decision and its exact version. | Supports decision-version control. | Must | Draft | Approval | TL-RULE-006 | TL-E02
TL-FR-011 | Functional | The solution shall prevent execution of a decision that does not match the approved version. | Central exact-version execution control. | Must | Draft | Execution validation | TL-RULE-006 | TL-E02
TL-FR-012 | Functional | The solution shall record the implementation or execution outcome. | Supports execution-result handling. | Must | Draft | Execution result | TL-RULE-009 | TL-E02
TL-FR-013 | Functional | The solution shall retain an audit trail of material actions and status changes. | Supports traceability and later review. | Must | Draft | Audit history | TL-RULE-010 | TL-E02
TL-FR-014 | Functional | The solution shall allow authorised users to review the full decision history. | Supports audit, compliance and QA review. | Should | Draft | Audit history | TL-RULE-010 | TL-E02
TL-FR-015 | Functional | The solution shall provide management reporting on case status, outcomes, exceptions and processing time. | Supports operational oversight and management information. | Should | Draft | Operational monitoring / reporting |  | TL-E02

## Business Rules Register
Rule ID | Rule Description | Rule Type | Trigger / Condition | Expected Behaviour | Exception Handling | Status | Related Requirement ID | Comments
TL-RULE-001 | A case must not proceed to assessment until all mandatory information is present or an authorised exception has been recorded. | Validation rule | Mandatory information is incomplete | Block progression to assessment | Allow progression only where the relevant policy permits it and an authorised exception is recorded | Draft | TL-FR-002, TL-FR-003 | TL-E02
TL-RULE-002 | The policy version used for assessment must be recorded with the decision. | Policy rule | Case is assessed | Record the policy version with the decision | Not specified in TL-E02 | Draft | TL-FR-004, TL-FR-005 | TL-E02
TL-RULE-003 | Each decision must include a recorded rationale. | Decision rule | Decision is proposed | Require a recorded rationale | Incomplete rationale prevents a complete decision record | Draft | TL-FR-006 | TL-E02
TL-RULE-004 | Cases meeting defined escalation criteria must be referred to an authorised approver. | Approval rule | Defined escalation criteria are met | Route the case to an authorised approver | Unauthorised approval must not satisfy the control | Draft | TL-FR-007, TL-FR-009 | TL-E02
TL-RULE-005 | A user must not approve a case they originated where separation of duties is required. | Segregation-of-duties rule | Originator attempts approval where SoD applies | Block self-approval | Case remains pending for an independent approver | Draft | TL-FR-008 | TL-E02
TL-RULE-006 | The approved decision must be the same version presented for execution. | Execution control | Execution is requested | Compare execution version with approved version and allow only an exact match | Block execution where the versions differ | Draft | TL-FR-010, TL-FR-011 | Central project control; TL-E02
TL-RULE-007 | An approval must not remain valid after a material case change. | Version-control rule | Material case change occurs after approval | Invalidate the earlier approval and require reassessment | Previous approval must not be used for execution | Draft | TL-FR-010, TL-FR-011 | TL-E02
TL-RULE-008 | A final decision must not be altered without creating a new controlled version. | Version-control rule | Final decision is altered | Create a new controlled decision version | Previous version remains part of the decision history | Draft | TL-FR-010 | TL-E02
TL-RULE-009 | The implementation result must be linked to the approved decision record. | Execution-result rule | Implementation or execution completes or fails | Link result to the approved decision record | Failed execution remains distinguishable from successful completion | Draft | TL-FR-012 | TL-E02
TL-RULE-010 | All material case actions must record the user, timestamp and action performed. | Audit rule | Material case action occurs | Record user, timestamp and action | Missing audit evidence represents a control gap | Draft | TL-FR-013, TL-FR-014 | TL-E02

## Exception Rules Register
Exception ID | Exception Rule | Trigger / Condition | Expected Behaviour | Required Approval / Control | Status | Related Requirement / Rule | Comments
TL-EX-001 | A case with missing mandatory information may proceed only where the relevant policy permits it and an authorised user records the reason. | Mandatory information is missing but progression is requested. | Allow progression only where policy permits it and the authorised reason is recorded. | Authorised exception and recorded reason. | Draft | TL-RULE-001, TL-FR-003 | TL-E02
TL-EX-002 | A policy exception must include a reason, evidence and approval by a user with the required authority. | A case requires a policy exception. | Record reason and evidence and obtain authorised approval before progression. | Approval by a user with required authority. | Draft | TL-RULE-004, TL-FR-007 | TL-E02
TL-EX-003 | A returned case must re-enter the controlled process at the appropriate earlier stage. | An approver returns a case for further work. | Route the case back to the appropriate controlled stage. | Controlled re-entry to the workflow. | Draft | TL-FR-009 | TL-E02
TL-EX-004 | A material change after approval must invalidate the earlier approval and require reassessment. | Material case information changes after approval. | Invalidate the earlier approval and require reassessment. | New approval required before execution. | Draft | TL-RULE-007, TL-FR-010, TL-FR-011 | TL-E02
TL-EX-005 | A failed execution must be recorded and must not be treated as a completed customer outcome. | Mortgage servicing returns an execution failure. | Record failure and keep the case distinguishable from successful completion. | Execution failure must be retained for investigation or further action. | Draft | TL-RULE-009, TL-FR-012 | TL-E02
TL-EX-006 | An expired or previously used execution authorisation must not permit execution. | Execution is attempted using expired or previously used authorisation. | Block execution and record the invalid attempt. | Authorisation validity must be checked before execution. | Draft | TL-FR-011 | TL-E02

## Non-Functional Requirements
NFR ID | Category | Requirement Description | Rationale | Priority | Status | Related Process / Control | Comments
TL-NFR-001 | Security | Access shall be restricted according to defined user roles and permissions. | Supports controlled access to case functions and information. | Must | Draft | Access control | TL-E02
TL-NFR-002 | Security | Customer information shall be protected in transit and at rest. | Supports confidentiality of customer information. | Must | Draft | Data protection | TL-E02
TL-NFR-003 | Security | Tenant or business-unit data shall remain isolated from unauthorised users. | Supports data segregation. | Must | Draft | Data isolation | TL-E02
TL-NFR-004 | Integrity | Decision evidence and audit records shall be protected against unauthorised alteration. | Supports integrity of decision evidence. | Must | Draft | Audit / evidence integrity | TL-E02
TL-NFR-005 | Auditability | Material actions shall be timestamped and attributable to a specific user or system. | Supports reconstruction of who or what performed each controlled action and when. | Must | Draft | Audit history | Referenced by TC-010; TL-E02
TL-NFR-006 | Auditability | The solution shall preserve sufficient evidence to reconstruct the decision path. | Supports audit, compliance and quality-assurance review. | Must | Draft | Decision reconstruction | Referenced by TC-010; TL-E02
TL-NFR-007 | Usability | The solution shall display clear validation and error messages. | Supports effective correction of invalid or incomplete actions. | Should | Draft | Validation / error handling | TL-E02
TL-NFR-008 | Usability | Core case pages shall be usable on standard desktop screen sizes. | Supports operational usability. | Should | Draft | Case user interface | TL-E02
TL-NFR-009 | Performance | Authorised case information should load within an agreed operational response time under normal conditions. | Supports operational responsiveness; target remains open. | Should | Draft | Case access / performance | Target not yet defined; TL-E02
TL-NFR-010 | Records management | The solution shall retain records according to the approved retention schedule. | Supports records-management obligations. | Must | Draft | Record retention | Retention period remains open; TL-E02
TL-NFR-011 | Supportability | The solution shall provide appropriate logging and monitoring for operational support. | Supports investigation and operational support. | Should | Draft | Operational support | TL-E02
TL-NFR-012 | Maintainability | Policy and rule changes shall be version controlled. | Supports controlled change to policy and decision logic. | Must | Draft | Policy / rule change control | TL-E02

## Business Requirements Register
Requirement ID | Requirement Description | Priority | Status | Source / Rationale | Comments
TL-BR-001 | The organisation shall apply a consistent and controlled process to mortgage-forbearance assessments. | Must | Draft | TL-E01 business problem and scope
TL-BR-002 | The organisation shall demonstrate which customer information, policy criteria and approvals supported each decision. | Must | Draft | Decision traceability requirement
TL-BR-003 | The organisation shall ensure that only appropriately authorised users approve controlled decisions. | Must | Draft | Approval-control requirement
TL-BR-004 | The organisation shall preserve a traceable record of the decision from intake through implementation. | Must | Draft | End-to-end traceability requirement
TL-BR-005 | The organisation shall reduce avoidable rework caused by missing information, incomplete checks or absent approval evidence. | Should | Draft | Operational-control requirement
TL-BR-006 | The organisation shall provide reliable management information on case volumes, outcomes, exceptions and delays. | Should | Draft | Management-information requirement

## Open Issues Register
Issue ID | Open Issue | Owner | Status | Impact / Notes
OI-001 | Confirm the complete set of mandatory intake information. | Business owner | Open | Impacts intake validation and TL-FR-002/TL-FR-003.
OI-002 | Confirm the approval thresholds and authority levels. | Policy owner | Open | Impacts approval routing and authority controls.
OI-003 | Confirm which case changes are considered material. | Risk and compliance | Open | Impacts approval invalidation and version control.
OI-004 | Confirm the authoritative source for each required data item. | Data and technology | Open | Impacts data sourcing and system-boundary definition.
OI-005 | Confirm the required retention period for decision evidence. | Legal and compliance | Open | Impacts TL-NFR-010.
OI-006 | Confirm measurable performance and availability targets. | Technology and operations | Open | Impacts TL-NFR-009 and service-level definition.